## Sheet1
Task Name | When to create | When to close | Tags to be used at Bug level | Next Tag at Bug level | Bug State | Next State | Feedback
Dev Analysis | Create when you start the analysis. Make sure you enter the Original Estimate (8 hours by default) and keep Remaining Estimate and Completed Estimate up to date. | As soon as the analysis is completed. | AIP |  | Active | Active | It would be helpful to developers if we add this task. Because there are few stories which takes hours of understanding. Along with it in bugs also we utilize some time to reproduce it so that hours we can added in this Dev analysis task.
Development | Create when the analysis is completed and you have sufficient details to start the development. Enter the estimate and keep Remaining and Completed estimate up to date. | When the development is completed and you are ready to write the Automated Unit Test Cases | DIP | Pending AUT | Active | Active | Required.
Automated Unit Test Case | When the development is completed and you are ready to write Automated Unit Test case and in the process of gathering the requirements. |  | AUT | Pending Checklist |  |  | Required.
PR Checklist | When the development is completed, close the Dev task before creating this. | When the Checklist is attached. | Checklist Preparation | Pending SSE Review | Active | Active | I don’t this so that this task is required. We generally attach the PR checklist with the PR itself and the reviewer always check whether the PR checklist is attached with the PR or not. So no any PR will be approved unless it has PR checklist attached with it.
SSE PR Review | Create this when any PR is assigned to you for review. Either the Developer will come to you and request to review the PR or SSE to check the Query. Enter the number of hours spent. | When the PR is reviewed and all the comments are closed. Assign the bug to TL for review. | SSE Review | Pending TL Review | Active | Active | Only one single Code review task will be enough.
TL PR Review | Create this when any PR is assigned to you for review. Item will be available in the below query. Enter the number of hours spent. | When the PR is reviewed and approved. | TL Review | PR Requested | Active | Active | Only one single Code review task will be enough.
Resolve PR Review Comments | If there are any PR comments. please keep the efforts logged in the system. | When the PR is reviewed and approved. | Resolve PR Comments | Pending SSE Review | Active | Active | Not required to create this task because it is itself a part of Development. It should be logged under development efforts.
Dev Support | JSE / SE / SSE / TL will create this task if you are supporting your colleague to fix the issue. | When the PR is approved by TL. |  |  | Active | Active | It would be useful. Someone who is helping can log their hours under this task.
QA Analysis | Create this during the analysis. | When the analysis is completed. |  |  | Triage/Active/New | Ready for Development / Rejected | N/A
Test Case Designing | When you start writing the test cases | When test cases are reviewed and approved |  |  | Active | Active | N/A
Test Case Review | When you start reviewing the test cases | When the test cases are reviewed and approved |  |  | Active | Active | N/A
Local QA | When you start the testing. As you have already completed the analysis, please update the estimate before starting the testing. | As soon you completed the testing. Close this task even if you assign back to developer. | Local QA | PR Approved | Resolved | Assign back to Dev if failed during the testing or resovled | N/A
| Dev to raise the PR and assign back to QA. |  | PR Requested
QA on Test Environment | When you start the testing on TST. Update the estimates | When it is closed | Remove all the tags before closing. |  | Ready to Test | Closed or Active if assigned back to Dev | N/A
On Hold
Fixed by Bug_id
E2E Testing
In Case of re-open
Re - Dev Analysis |  |  | Re - Dev Analysis |  |  | Useful
Re - Development | Conflicts resolve, re-open |  | Re - Development |  |  | Useful
Re - SSE PR Review |  |  | Re - SSE PR Review |  |  | Only one single Code review task will be enough.
Re - TL PR Review |  |  | Re - TL PR Review |  |  | Only one single Code review task will be enough.
Re - Local QA |  |  | Re - Local QA |  |  | Useful
Re - QA on Test Environment |  |  | Re - QA on Test Environment |  |  | N/A

## Sheet2
Task Name
Analysis
Development
Peer Review
Support
Evidence
Re Development
Re Analysis
Deployment

## Sheet3
Task Name | When to create | When to close | Tags to be used at Bug level | Next Tag at Bug level | Bug State | Next State
Dev Analysis | Create when you start the analysis. Make sure you enter the Original Estimate (8 hours by default) and keep Remaining Estimate and Completed Estimate up to date. | As soon as the analysis is completed. | AIP |  | Active | Active
Development | Create when the analysis is completed and you have sufficient details to start the development. Enter the estimate and keep Remaining and Completed estimate up to date. | When the development is completed and you are ready to write the Automated Unit Test Cases | DIP | Pending AUT | Active | Active
Automated Unit Test Case | When the development is completed and you are ready to write Automated Unit Test case and in the process of gathering the requirements. |  | AUT | Pending Checklist
PR Checklist | When the development is completed, close the Dev task before creating this. | When the Checklist is attached. | Checklist Preparation | Pending SSE Review | Active | Active
SSE PR Review | Create this when any PR is assigned to you for review. Either the Developer will come to you and request to review the PR or SSE to check the Query. Enter the number of hours spent. | When the PR is reviewed and all the comments are closed. Assign the bug to TL for review. | In SSE Review | Pending TL Review | Active | Active
TL PR Review | Create this when any PR is assigned to you for review. Item will be available in the below query. Enter the number of hours spent. | When the PR is reviewed and approved. | In TL Review | PR Requested | Active | Active
Resolve PR Review Comments | If there are any PR comments. please keep the efforts logged in the system. | When the PR is reviewed and approved. | Resolve PR Comments | Pending SSE Review | Active | Active
Dev Support | JSE / SE / SSE / TL will create this task if you are supporting your colleague to fix the issue. | When the PR is approved by TL. |  |  | Active | Active
QA Analysis | Create this during the analysis. | When the analysis is completed. |  |  | Triage/Active/New | Ready for Development / Rejected
Test Case Designing | When you start writing the test cases | When test cases are reviewed and approved |  |  | Active | Active
Test Case Review | When you start reviewing the test cases | When the test cases are reviewed and approved |  |  | Active | Active
Local QA | When you start the testing. As you have already completed the analysis, please update the estimate before starting the testing. | As soon you completed the testing. Close this task even if you assign back to developer. | Local QA | PR Approved | Resolved | Assign back to Dev if failed during the testing or resovled
| Dev to raise the PR and assign back to QA. |  | PR Requested
QA on Test Environment | When you start the testing on TST. Update the estimates | When it is closed | SIT Done |  | Ready to Test | Closed or Active if assigned back to Dev
On Hold
Fixed by Bug_id
Yourname - Sprint Kickoff | Current Sprint
Yourname - Sprint Estimate | Next Sprint but the task has to be created in the currect Sprint
Yourname - Retrospective | Current Sprint
Yourname - Daily Standup | Current Sprint
Yourname - Planning | Next Sprint but the task has to be created in the currect Sprint
E2E Testing
In Case of re-open
Re - Dev Analysis |  |  | Re - Dev Analysis
Re - Development | Conflicts resolve, re-open |  | Re - Development
Re - SSE PR Review |  |  | Re - SSE PR Review
Re - TL PR Review |  |  | Re - TL PR Review
Re - Local QA |  |  | Re - Local QA
Re - QA on Test Environment |  |  | Re - QA on Test Environment
Re - QA Analysis